## Sprint 1
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 64 | 64
1 | 39 | 39
2 | 0 | 0
0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 14 | 14
19 | 14 | 14
18 | 14 | 14
17 | 13 | 14
16 | 13 | 14
15 | 13 | 14
14 | 13 | 14
13 | 11 | 14
12 | 11 | 13
11 | 10 | 13
10 | 9 | 12
9 | 9 | 10
8 | 8 | 10
7 | 7 | 8
6 | 6 | 13
5 | 5 | 10
4 | 4 | 8
3 | 3 | 5
2 | 2 | 3
1 | 1 | 2
0 | 0 | 0

## Sprint 2
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 64 | 64
1 | 39 | 39
2 | 0 | 0
| 0 | 0
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 19 | 18
19 | 18 | 18
18 | 18 | 18
17 | 17 | 18
16 | 16 | 18
15 | 15 | 18
14 | 14 | 18
13 | 13 | 18
12 | 12 | 17
11 | 11 | 17
10 | 10 | 17
9 | 9 | 15
8 | 8 | 13
7 | 7 | 10
6 | 6 | 10
5 | 5 | 10
4 | 4 | 5
3 | 3 | 5
2 | 2 | 0
1 | 1 | 0
0 | 0 | 0